## Sheet1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Viết file tổng hợp + phân chia công việc | 2001-09-29 | 2021-09-30 | 100% | Ánh Ngọc | - | - | - | -
Header | 2021-10-01 |  | 80% | Ánh Ngọc |  |  | 95% | Dev2
Logo | 2021-10-01 | 2021-10-01 | 100% |  |  |  | 50% | Nhật Trường
Right | 2021-10-01 | 2021-10-01 | 100% |  |  |  | 90% | Nhật Trường
Nav | 2021-10-01 | 2021-10-01 | 100% |  |  |  | 100% | Nhật Trường
Search form | 2021-10-01 | 2021-10-01 | 100% |  |  |  | 90% | Nhật Trường
Dark theme | 2021-10-01 | 2021-10-01 | 100% |  |  |  | 80% | Nhật Trường
Responsive |  |  | 0%
Carousel | 2021-10-02 |  | 80% | Nguyên Phi |  |  | 80% | Dev2
Content | 2021-10-02 | 2021-10-02 | 100% |  |  |  | 100% | Nguyên Phi
Background | 2021-10-02 | 2021-10-02 | 100% |  |  |  | 100% | Nguyên Phi
Responsive |  |  | 0%
About | 2021-10-02 |  | 80% | Nguyên Phi |  |  | 80% | Nguyên Phi
Content | 2021-10-02 | 2021-10-02 | 100% |  |  |  | 100%
Responsive |  |  | 0%
Book | 2021-10-02 |  | 67% | Ánh Ngọc
Image (Left) | 2021-10-02 | 2021-10-02 | 100%
Content (right) | 2021-10-02 | 2021-10-02 | 100%
Responsive |  |  | 0%
News |  |  | 0% | Ánh Ngọc
Grid Layout |  |  | 0%
Hover |  |  | 0%
Responsive |  |  | 0%
Type |  |  | 0% | Nguyên Phi
Content |  |  | 0%
Responsive |  |  | 0%
Number |  |  | 0% | Ánh Ngọc
Banner |  |  | 0%
Number |  |  | 0%
Responsive |  |  | 0%
Video |  |  | 0% | Nguyên Phi
Content |  |  | 0%
Responsive |  |  | 0%
Post |  |  | 0% | Nguyên Phi
Content |  |  | 0%
Responsive |  |  | 0%
Testinomial |  |  | 0% | Ánh Ngọc
Item |  |  | 0%
Carousel |  |  | 0%
Responsive |  |  | 0%
Footer |  |  | 0% | Nguyên Phi
Top |  |  | 0%
Grid Layout |  |  | 0%
Form |  |  | 0%
Bottom |  |  | 0%
Responsive |  |  | 0%
Back to top |  |  | 0% | Nguyên Phi